## Sheet1
ID | Feature | Tasking | Status | Assigned To | User Story
1 | Map Rendering | Evan | High Priority | Sprint 1 | As a player, I want to be able to have my avatar's location on a map mirror my real world location.
2 | GPS Functionality | Evan | High Priority | Sprint 1 | As a player, I want to be able to have my avatar's location on a map mirror my real world location.
3 | Inventory System | Ozzy | Mid Priority | Sprint 1 | As a player, I want to be able to pick up items on the map.
4 | Crafting System | Ozzy | Low Priority | Sprint 1 | As a player, I want to be able to play a game and, based on my success at the game, get better or poorer items.
5 | Points of Interest | Ayanna | High Priority | Sprint 1 | As a player, I want to be able to rank up my avatar based on going to a place in the real world.
6 | Suggestion of POI |  | Low Priority | Sprint 3 | As a player, I want to be able to rank up my avatar based on going to a place in the real world.
7 | Avatar Customize |  | Mid Priority | Sprint 2 | As a player, I want to be able to customize the look of my avatar.
8 | Multiple Pets/Reset |  | Stretch | If possible | As a player, I want to be able to customize the look of my avatar.
9 | Statistics |  | Mid Priority | Sprint 2 | As a player, I want to be able to play a game and, based on my success at the game, get better or poorer items.
10 | Unboxing items |  | Mid Priority | Sprint 2 | As a player, I want to be able to pick up items on the map.
11 | Level System | Ozzy | Mid Priority | Sprint 2 | As a player, I want to be able to play a game and, based on my success at the game, get better or poorer items.
12 | Avatar Rendering | Nashaly | High Priority | Sprint 1 | As a player, I want to be able to customize the look of my avatar.
13 | Appointment System |  | Low Priority | Sprint 3 | As a player, I want to be able to organize events in my calendar and be rewarded by the game for completing or attending them.
14 | Multiplayer/Database |  | Stretch | If possible
15 | Home POI |  | Stretch | If possible
16 | UI/Buttons | Tyrone | High Priority | Sprint 1 | As a player, I want to be able to have my avatar's location on a map mirror my real world location.
17 | Localization? | Ozzy | Stretch | If possible
18 | Achievements |  | Stretch | If possible
19 | Minigames | Ozzy | Mid Priority | Sprint 2 | As a player, I want to be able to play a game and, based on my success at the game, get better or poorer items.